## Site_Costs
LCS2 Site and Project Cost Analysis
E.L. Swenson 8/18/2019
Component Costs
|  | Material ($s) |  | Component Labor (hrs.)
|  | Organization |  | Organization |  |  |  | Labor ($s)
|  | Pepsi | LFSA | LFSA | TPWD | Yantis HS | Total | Total
Component |  | In-Kind | Cash | In-Kind |  |  |  | In-Kind |  | Total
Spawning Beds |  | 3 | 4.3323 | 0.73333 | 0.5 | 0.7 | 1.9333 | 32.2 |  | 39.5323
Minnow Factory |  | 0 | 51.5355 | 1.8 | 1 | 2.3 | 5.3667 | 79.4 |  | 130.9355
Habitat Protection Fence |  | 0 | 31.7886 | 2.65 | 2.8125 | 1.75 | 7.2125 | 132.7 |  | 164.4886
T-Habs |  | 15 | 15.307 | 1.1333 | 1 | 2.6 | 4.7333 | 70.4 |  | 100.707
T-Habs - Double Stack Kit |  | 0 | 32.147 | 0.53333 | 0.5 | 0 | 1.0333 | 21.6 |  | 53.747
Single Site Costs
|  | Material ($s) |  | Labor ($s) |  |  |  | All Mat. & Labor ($s) |  | Total
| Qty./Site | In-Kind | Cash | LFSA ($18) | TPWD ($24) | Yantis HS ($10) | Total | In-Kind | Cash | All
Spawning Beds | 8 | 24 | 34.6587 | 105.6 | 96 | 56 | 257.6 | 281.6 | 34.6587 | 316.2587
Minnow Factory | 4 | 0 | 206.142 | 129.6 | 96 | 92 | 317.6 | 317.6 | 206.142 | 523.742
Habitat Protection Fence | 8 | 0 | 254.3088 | 381.6 | 540 | 140 | 1061.6 | 1061.6 | 254.3088 | 1315.9088
T-Habs | 20 | 300 | 306.1394 | 408 | 480 | 520 | 1408 | 1708 | 306.1394 | 2014.1394
T-Habs - Double Stack Kit | 5 | 0 | 160.7349 | 48 | 60 | 0 | 108 | 108 | 160.7349 | 268.7349
| Site Totals | 324 | 961.9838 | 1072.8 | 1272 | 808 | 3152.8 | 3476.8 | 961.9838 | 4438.7838
Total Project Cost - (6) Sites
|  | Material |  | Labor ($s) |  |  |  | All Mat. & Labor ($s) |  | Total
Component |  | In-Kind | Cash | LFSA ($18) | TPWD ($24) | Yantis HS ($10) | Total | In-Kind | Cash | All
Spawning Beds |  | 144 | 207.9523 | 633.6 | 576 | 336 | 1545.6 | 1689.6 | 207.9523 | 1897.5523
Minnow Factory |  | 0 | 1236.852 | 777.6 | 576 | 552 | 1905.6 | 1905.6 | 1236.852 | 3142.452
Habitat Protection Fence |  | 0 | 1525.8528 | 2289.6 | 3240 | 840 | 6369.6 | 6369.6 | 1525.8528 | 7895.4528
T-Habs |  | 1800 | 1836.8364 | 2448 | 2880 | 3120 | 8448 | 10248 | 1836.8364 | 12084.8364
T-Habs - Double Stack Kit |  | 0 | 964.4091 | 288 | 360 | 0 | 648 | 648 | 964.4091 | 1612.4091
| Project Totals | 1944 | 5771.9027 | 6436.8 | 7632 | 4848 | 18916.8 | 20860.8 | 5771.9027 | 26632.7027
Small Grant Cost - 6 Sites
|  | Material |  | Labor ($s) - (All In-Kind) |  |  |  | All Mat. & Labor ($s) |  | Total
Component |  | In-Kind | Cash | LFSA ($18) | TPWD ($24) | Yantis HS ($10) | Total | In-Kind | Cash | All
Spawning Beds |  | 144 | 207.9523 | 633.6 | 576 | 336 | 1545.6 | 1689.6 | 207.9523 | 1897.5523
Minnow Factory |  | 0 | 1236.852 | 777.6 | 576 | 552 | 1905.6 | 1905.6 | 1236.852 | 3142.452
Habitat Protection Fence |  | 0 | 1525.8528 | 2289.6 | 3240 | 840 | 6369.6 | 6369.6 | 1525.8528 | 7895.4528
| Small Grant Totals | 144 | 2970.6571 | 3700.8 | 4392 | 1728 | 9820.8 | 9964.8 | 2970.6571 | 12935.4571
Small Grant Labor Contributions
Labor (hrs.) - (All In-Kind)
| Component |  |  | LFSA | TPWD | Yantis HS | Total
| Spawning Beds |  |  | 35.2 | 24 | 33.6 | 92.8
| Minnow Factory |  |  | 43.2 | 24 | 55.2 | 122.4
| Habitat Protection Fence |  |  | 127.2 | 135 | 84 | 346.2
| Small Grant Totals |  |  | 205.6 | 183 | 172.8 | 561.4
Values used for Small Grant Application

## LCS^2_Components
LCS2 Detailed Component Cost Analysis | [11 empty] | 20 | 10 | 18 | 24 | 5.1062
|  |  | Material |  | Labor |  | Labor (hrs.)/ unit | [8 empty] | 231 | 46656
Component | Source | Desc. | In-Kind | Cash | In-Kind | Cash | LFSA | TPWD | Yantis HS | Total | Total
Spawning Beds | LFSA/TPWD/Yantis HS/ Pepsi |  | 3 | 4.3323 | 31.4667 | 0 | 0.73333 | 0.5 | 0.7 | 1.9333 | 35.799
Barrels | LFSA | Pepsi - Beverage Barrels | 3 | [7 empty] | Local cost for equivalent barrel $15 with 5 beds/barrel
Bricks | LFSA | Lowes - Oldcastle Red Cored Brick |  | 2.72 | [6 empty] | (4) bricks/bed
Pea Gravel | LFSA | Local Supply |  | 0.61394 | [6 empty] | (2) 5 gal. buckets/bed Gravel $62/yd. - 5.10" Depth in ring
Zip Ties | LFSA | Lowes - Zip Ties |  | 0.9984 | [6 empty] | (8) ties/bed
Labor | LFSA | Order & P/U Materials (10 units) |  |  | 4.0667 |  | 0.13333 |  |  | 0.13333 | 100 mile roundtrip, $.50/mile $50, Total travel & unload 4 adult hours 30 barrels/load
Labor | LFSA | Coordinate build/storage |  |  | 1.2 |  | 0.2 |  |  | 0.2 | Coordinate build/storage 3 Adult hrs./30
Labor | Yantis HS | Construct Factories |  |  | 3 |  |  |  | 0.3 | 0.3 | Slice Barrel 15 min/barrel 5 hoops= 3 min. asm bricks to ring 15 min = total 18 min
Labor | LFSA | Deploy in Lake |  |  | 7.2 |  | 0.4 |  |  | 0.4 | Gather, load, deploy and return 2 adult people x 4 hours / 20 beds
Labor | TPWD | Deploy in Lake |  |  | 12 |  |  | 0.5 |  | 0.5 | Load, deploy and return 2 Agency people x 5 hours / 20 beds
Labor | Yantis HS | Deploy in Lake |  |  | 4 |  |  |  | 0.4 | 0.4 | Load, deploy and return 2 Students people x 4 hours / 20 bed
Minnow Factory | LFSA/TPWD/ Yantis HS |  |  | 51.5355 | 117.4 | 0 | 1.8 | 1 | 2.3 | 5.3667 | 168.9355
Tubing | LFSA | Lowes -ADS 4-in x 100-ft Corrugated Perforated Pipe |  | 36.675 | [6 empty] | (2) Factories/ roll
Cable Ties | LFSA | Lowes - Utilitech 800-Pack 4-in Nylon Cable Ties |  | 1.0925 | [6 empty] | 16 ties /Factory
Electrical Tape | LFSA | Lowes - Utilitech 10-Pack 60-ft Electrical Tape |  | 1.356 | [6 empty] | 2 Rolls/Factory
Rope | LFSA | Lowes - Secure Line 0.1875-in x 100-ft Braided Polypropylene Rope |  | 1.647 | [6 empty] | 15'/Factory
Poultry Fencing | LFSA | Home Depot - 2 ft. x 25 ft. Green Poultry Hex Fence |  | 8.725 | [6 empty] | 2 Factories/ roll
Bricks | LFSA | Lowes - Oldcastle Red Cored Brick |  | 2.04 | [6 empty] | 3 bricks/factory
Labor | LFSA | Order & P/U Materials (10 units) |  |  | 21.6 |  | 0.13333 |  |  | 0.13333 | Ordering, Traveling to get material and delivery to build site/30 units 12 @ 18 = 216
Labor | LFSA | Coordinate build/storage |  |  | 18 |  | 0.066667 |  |  | 0.33333 | Estimate 2 Adult hours /30 units
Labor | Yantis HS | Construct Factories |  |  | 15 |  |  |  | 1.5 | 1.5 | Cut tube, subassembly, assemble, wrap, tie 1.5 hr./factory
Labor | LFSA | Deploy in Lake |  |  | 28.8 |  | 1.6 |  |  | 1.6 | Gather, load, deploy and return 4 adult people x 4 hours / 10 factories
Labor | TPWD | Deploy in Lake |  |  | 18 |  |  | 1 |  | 1 | Load, deploy and return 2 adult x 5 hours / 10 Factories
Labor | Yantis HS | Deploy in Lake |  |  | 16 |  |  |  | 0.8 | 0.8 | Load, deploy and return 2 Students people x 4 hours / 10 factories
Habitat Protection Fence | LFSA/TPWD/Yantis HS |  |  | 31.7886 | 108.9 | 0 | 2.65 | 2.8125 | 1.75 | 7.2125 | 140.6886
HPF 3' D x 4' H | LFSA | Fence, Posts and clips |  | 28.0686 | [6 empty] | See detail on Hoops sheet for fence, posts and clips
Post Markers | LFSA | Lowes - PVC Pipe |  | 2.72 | [6 empty] | (4) /hoop
Site Signage | LFSA | Local Supply |  | 1 | [6 empty] | 3/16" material
Labor | LFSA | Order & P/U Materials (20 units) |  |  | 1.8 |  | 0.1 |  |  | 0.1 | 2 adult hours 20 hoops/load
Labor | LFSA | Coordinate build/storage |  |  | 1.2 |  | 0.05 |  |  | 0.05 | Coordinate build/storage 1 Adult hrs./20
Labor | Yantis HS | Construct Factories |  |  | 2.3 |  |  | 0.8125 |  | 0.8125 | Design (3 Hrs.), program (3 hrs.) and torch (.5 hrs.)/signs
Labor | LFSA | Deploy in Lake |  |  | 45 |  | 2.5 |  |  | 2.5 | Gather, load, deploy and return 4 adult people x 5 hours / 8 hoops | 12.5664
Labor | TPWD | Deploy in Lake |  |  | 33.6 |  |  |  | 1.75 | 1.75 | Load, deploy and return 2 Agency people x 7 hours / 8 hoops
Labor | Yantis HS | Deploy in Lake |  |  | 25 |  |  | 2 |  | 2 | Load, deploy and return 4 Students people x 4 hours / 8 hoops
T-Habs | LFSA/TPWD/Yantis HS/ Pepsi |  | 15 | 15.307 | 69.6667 | 0 | 1.1333 | 1 | 2.6 | 4.7333 | 84.9736
Barrels | LFSA | Pepsi - Beverage Barrels | 15 | [7 empty] | Local cost for equivalent barrel $15
Tubing | LFSA | Rainbird 1/2" Tubing |  | 15 | [6 empty] | See detail on Attractor sheet for details
Pea Gravel | LFSA | Local Supply |  | 0.30697 | [6 empty] | (1) 5 gal. buckets/bed Gravel $62/yd.
Labor | LFSA | Order & P/U Materials (10 units) |  |  | 4.0667 |  | 0.13333 |  |  | 0.13333 | 100 mile roundtrip, $.50/mile $50, Total travel & unload 4 adult hours 30 barrels/load
Labor | LFSA | Coordinate build/storage |  |  | 1.2 |  | 0.2 |  |  | 0.2 | Coordinate build/storage 2 Adult hrs./10
Labor | Yantis HS | Construct T-Habs |  |  | 10 |  |  |  | 1 | 1 | Mark holes, drill holes and assemble tubing 1 hr.
Labor | LFSA | Deploy in Lake |  |  | 14.4 |  | 0.8 |  |  | 0.8 | Gather, load, deploy and return 2 adult people x 4 hours / 10 T-Habs
Labor | TPWD | Deploy in Lake |  |  | 24 |  |  | 1 |  | 1 | Load, deploy and return 2 Agency people x 5 hours / 10 T-Habs
Labor | Yantis HS | Deploy in Lake |  |  | 16 |  |  |  | 1.6 | 1.6 | Load, deploy and return 4 Students people x 4 hours / 10 T-Habs
T-Habs - Double Stack Kit | LFSA/TPWD/Yantis HS |  | 0 | 32.147 | 22.8 | 0 | 0.53333 | 0.5 | 0 | 1.0333 | 54.947
Cable | LFSA | Local Supply |  | 24 | [6 empty] | 1/2" Vinyl Coated Galvanized Steel Cable estimate $2/ft.)
Cable Clamps | LFSA | Local Supply |  | 4 | [6 empty] | (4) 1/2" Galvanized Cable Clamps
Pea Gravel | LFSA | Local Supply |  | 0.30697 | [6 empty] | (1) 5 gal. buckets/bed Gravel $62/yd.
Urethane Foam | LFSA | Lowes - Dow 12-oz Spray Foam Insulation |  | 3.84
Labor | LFSA | Order & P/U Materials (10 units) |  |  | 1.8 |  | 0.033333 |  |  | 0.033333 | Order and p/u adult 1 hour/30
Labor | LFSA | Deploy in Lake |  |  | 9 |  | 0.5 |  |  | 0.5 | Install 1 adult .5 hrs.
Labor | TPWD | Deploy in Lake |  |  | 12 |  |  | 0.5 |  | 0.5 | Install 1 agency .5 hrs.

## Spawning_Beds
Spawning Bed Configuration
Plastic Barrel
2' dia. X 3' Long
Slice both ends off
Make (5) 6" high rings
Bricks secured to ring with zip tie (4)

## Minnow_Factory
Minnow Factory Design Detail

## HPF
Habatat Protection Fence (HPF)Cost Estimate
11/29/18 ELS
•One of the most versatile wire products made
•Sturdy welds keep mesh spacing uniform and distortion free
•Vertical wires are cut flush top and bottom to prevent snagging
•Galvanized before welding for longer life
•2 in. x 4 in. square
Description | 3' Dia x 3' High | Description | 3' Dia x 4' High | Description | 3' Dia x 6' High
Height: 36 in. |  | Height: 48 in. |  | Height: 72 in.
Length: 100 ft. |  | Length: 100 ft. |  | Length: 100 ft.
Mesh: 2 in. x 4 in. |  | Mesh: 2 in. x 4 in. |  | Mesh: 2 in. x 4 in.
Brand: Red Brand |  | Brand: Red Brand |  | Brand: Red Brand
Product Type: Welded Wire |  | Product Type: Welded Wire |  | Product Type: Welded Wire
Manufacturer Part Number 84066 |  | Manufacturer Part Number 84066 |  | Manufacturer Part Number 84066
Wire Roll | 54.99 | Wire Roll | 57.99 | Wire Roll | 129.99
Wire 10'/Hoop | 5.499 | Wire 10'/Hoop | 5.799 | Wire 10'/Hoop | 12.999
5' T Post (3) | 3.19 | 6' T Post (3) | 3.59 | 8' T Post (3) | 6.1
Fence Clips (2) | 4.59 | Fence Clips (2) | 4.59 | Fence Clips (2) | 4.59
Top-3' Hoop | 1.6497 | Top-4' Hoop | 2.3196 | Top-6' Hoop | 7.7994
Hoop Cost | 25.8987 |  | 28.0686 |  | 48.2784
Hoops/Site | 2 |  | 2 |  | 2
Cost/Site | 51.7974 |  | 56.1372 |  | 96.5568
Cost - 6 Sites | 310.7844 |  | 336.8232 |  | 579.3408
Total Material Cost | 1226.9484
Unidentified (15%) | 184.0423
Total Cost Estimate | 1410.9907
Hoops/Site | 3 |  | 3 |  | 3
Cost/Site | 77.6961 |  | 84.2058 |  | 144.8352
Cost - 6 Sites | 466.1766 |  | 505.2348 |  | 869.0112
Total Material Cost | 1840.4226
Unidentified (15%) | 276.0634
Total Cost Estimate | 2116.486
Hoops/Site | 4 |  | 4 |  | 4
Cost/Site | 103.5948 |  | 112.2744 |  | 193.1136
Cost - 6 Sites | 621.5688 |  | 673.6464 |  | 1158.6816
Total Material Cost | 2453.8968
Unidentified (15%) | 368.0845
Total Cost Estimate | 2821.9813

## T-Habs
TPWD Attractor Project Cost Estimate
11/29/18 ELS
Barrels are containers for Pepsi Syrup and available for free with prior notice for pickup.
500' Roll | 45
3 Attractors/Roll | 15
Cost/Barrel | 15
# of Barrels | 220
Total Material Costs | 3300
Tools & Unidentified | 200
3500